## Hoja1
Name with () is assistant
Name of the task | Name who has done | Estimated time (hours) | Time elapsed (hours)
Add-> **Update "Big 1" | Elliot Jimenez | 1 | 1
Add-> Move pacman with sprites | Elliot Jimenez | 2 | 3 | **Update "Big 1": | **Modules Levels
Add-> ModuleFadeToBlack | Elliot Jimenez | 0.2 | 0.2 | Animation.h | Added ModuleWelcome.h
Add-> **Modules Levels | Elliot Jimenez | 1 | 1 | Application.h | Added ModuleWelcome.cpp
Add-> ModuleSound | Elliot Jimenez | 1 | 2 | Application.cpp | Added ModuleLevel1.h
Add-> Musics | Elliot Jimenez | 0.8 | 1 | Globals.h | Added ModuleLevel1.cpp
Add-> Sprite level | Elliot Jimenez | 0.5 | 0.5 | Globals.cpp | Added ModuleLevel2.h
Add-> Moviment Ms Pacman with collisions | Elliot Jimenez | 5 | 6 | log.cpp | Added ModuleLevel2.cpp
Add-> Intro Ms Pacman | Elliot Jimenez | 4 | 4 | new* Main.cpp | Added ModuleCongratulations.h
Fixed-> Moviment Ms Pacman | Elliot Jimenez (Gerard) | 6 | 14 | MemLeaks.h | Added ModuleCongratulations.cpp
Add-> ModuleCollisions and implement it | Elliot Jimenez | 2 | 2 | Module.h | Added ModuleFadeToBlack.h
Add-> MusicStats implemented | Elliot Jimenez | 1 | 1 | ModuleBackground,h | Added ModuleFadeToBlack.cpp
Fixed-> Camara don't move | Elliot Jimenez | 0.1 | 0.1 | ModuleBackground,cpp
Edit-> ModuleInput and Player input | Elliot Jimenez | 0.5 | 0.5 | ModuleInput.h
Add-> Moviment Ghost red like the game | Elliot Jimenez | 3 | 10 | ModuleInput.cpp
Add-> More sounds | Elliot Jimenez | 0.1 | 0.1 | ModulePlayer.h
Add-> ModuleScore | Elliot Jimenez | 1 | 2 | ModulePlayer.cpp
Add-> Move ghost blue like red and fixed bugs | Elliot Jimenez | 2 | 3 | ModuleRender.h
Add-> Moviment Ghost Pink like the game | Elliot Jimenez (Arnau) | 2 | 3 | ModuleRender.cpp
Add-> Change lvl1 for lvl 3 | Elliot Jimenez | 0.2 | 0.2 | ModuleTextures.h
Add-> HAIG SCORE | Elliot Jimenez | 0.5 | 0.5 | ModuleTextures.cpp
Add-> Time fixing bugs | Elliot Jimenez | 6 | 20 | ModuleWindow.h
Add-> Sprite move pills red | Gerard Gil | 3 | 4 | ModuleWindow.cpp
Fixed-> Sprites stats and pills | Gerard Gil | 2 | 3 | p2Point.h
Add-> Added names on the welcome screen | Gerard Gil | 1 | 1
Add-> Game Over | Gerard Gil | 0.5 | 0.5
Add-> ghost moves inside the center | Gerard Gil | 2 | 2
Add-> Added names on the welcome screen | Gerard Gil | 1 | 1
Add-> Ready and Ghosts starts with the player | Gerard Gil | 1 | 1
Add-> MsPacman lives display | Gerard Gil (Albert) | 0.5 | 0.5
Add-> Animation and spites of level 1 | Gerard Gil | 1 | 1
Edit-> Times and Sprites | Gerard Gil | 7 | 20
Add-> Time fixing bugs | Gerard Gil | 6 | 15
Add-> print pills and can eat | Albert Llopart | 1 | 2
Add-> lvl 1 win condition | Albert Llopart | 1 | 1
Add-> Moviment ghost with collisions | Albert Llopart (Elliot) | 7 | 10
Change-> README for the prototype | Albert Llopart | 1 | 1
Add-> Gode Mode | Albert Llopart (Elliot) | 0.5 | 1
Add-> Pause when eatting a ghost | Albert Llopart | 2 | 3
Add-> Time fixing bugs | Albert Llopart | 6 | 2
Add-> Moviment Ghost Orange like the game | Alfonso Sanchez | 1 | 3
Add-> Create a module.h for all ghost | Alfonso Sanchez | 1 | 1
Add-> TILE 2 | Alfonso Sanchez | 2 | 2
Add-> ModuleLevel 3 and 4 | Alfonso Sanchez (Elliot) | 0.5 | 0.5
Add-> Move Up and Down | Alfonso Sanchez | 0.1 | 0.1
Add-> Animation down and up | Alfonso Sanchez (Elliot) | 0.5 | 1
Add-> Tile 1 | Alfonso Sanchez | 2 | 2
Add-> Time fixing bugs | Alfonso Sanchez | 6 | 4
Add-> Animation Big Point | Arnau Morgado | 1 | 1
Add-> Lives implemented | Arnau Morgado | 1 | 1
Add-> Now You can play Again | Arnau Morgado (Elliot) | 1 | 3
Add-> Create moviment random og the ghots | Arnau Morgado (Elliot) | 2 | 3
Add-> Can use tunels | Arnau Morgado (Elliot) | 1 | 4
Add-> Time fixing bugs | Arnau Morgado | 6 | 2
TOTAL |  | 108.5 | 171.7
Graphics of time i number of tasks
Name | Nº of Tasks | Total Estimed time | Total Time elapsed
Elliot Jimenez | 28 | 52.4 | 97.6
Gerard Gil | 10 | 31 | 63
Albert Llopart | 7 | 19 | 20.5
Alfonso Sanchez | 7 | 13.1 | 13.6
Arnau Morgado | 6 | 14 | 17
TOTAL | 58 | 108.5 | 171.7